## PO DAILY REPORTS
CONSTRUCTION |  | Officer ID | a0001 |  |  |  |  | DAY | 21
PROJECT |  | Officer NAME | NANA KWESI SAFO |  |  |  |  | MONTH | FEB
PROGRESS |  | PHONE NUMBER | 0541836219 |  |  |  |  | DATE | 2024-02-21
v4.0
| id | reporting_date | officer_id | (owner_name) | location | house_number | (activity) | sector | GPS_area | (Officer_comment) | percentage_of_workdone | status
| 1 | 2024-02-21 | A0001 | ACKAH PETER | SPINTEX | GPS-513-87 | EXCAVATION | 1 | 1.41 |  | 40 | ONGOING
| 2 | 2024-02-21 | A0001 | ACKAH PETER | SPINTEX | GPS-513-87 | FRAMING | 1 | 1.41
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
|  |  | owner_name | location | GPS_address | GPS_area | sub_activity
|  |  | KWAKU BOATENG | LABONE | GPS-902-20 | 0.45 | SITE PREPARATION
|  |  | KOJO WILLSON | TESHIE | GPS-752-32 | 0.86 | EXCAVATION
|  |  | ALIDU BAWA | TAIFA | GPS-752-38 | 1.02 | FOUNDATION
|  |  | KWAME BAWA | DOME | GPS-850-16 | 0.54 | FRAMING
|  |  | MOHAMMED BONABA | TAIFA | GPS-551-42 | 0.74 | MASONRY
|  |  | KWASI FRANK | KASOA | GPS-171-67 | 4.77 | ELECTRICAL AND PLUMBING WORK
|  |  | ABDUL MALIK | LABONE | GPS-665-33 | 0.57 | ROOFING
|  |  | ACKAH PETER | SPINTEX | GPS-513-87 | 1.41 | EXTERIOR FINISHING
|  |  | HARUNA FARIKU | TAIFA | GPS-845-47 | 1.15 | HEATING AND COOLING WORK
|  |  | ABDUL MALIK | KANESHIE | GPS-162-14 | 2.3 | INTERIOR FINISHING
|  |  | ADU ENOCK | WEIJA | GPS-966-10 | 1.03 | WOODWORK AND FIXTURE FITTINGS
|  |  | YEBOAH MOSES | WEIJA | GPS-573-25 | 2.06 | WATERPROOFING
|  |  | AMOS HINNEH | TESHIE | GPS-847-21 | 0.66 | PAINTING
|  |  | AMOS HINNEH | TAIFA | GPS-735-12 | 0.27
|  |  | AMOS HINNEH | LAPAZ | GPS-639-48 | 0.12
|  |  | AMOS HINNEH | DOME | GPS-900-38 | 1.12
|  |  | TANKO ISMAILA | TAIFA | GPS-205-35 | 1.16
|  |  | TWENE KWABENA | WEIJA | GPS-973-25 | 0.91
|  |  | KWAME TAKYI | TAIFA | GPS-164-40 | 0.59
|  |  | KWAME TAKYI | KANESHIE | GPS-776-74 | 0.66
|  |  | TWETRIE YAW | WEIJA | GPS-678-75 | 0.51
|  |  | KOFI YEBOAH | LABONE | GPS-771-75 | 1.55
|  |  | ISAAC BAFFOE | POKUASE | GPS-221-67 | 0.1
|  |  | ISAAC BAFFOE | TAIFA | GPS-470-10 | 0.27 | percentage_of_work_done | MONTH
|  |  | ISAAC BAFFOE | LABONE | GPS-508-89 | 1.22 | 20 | JAN
|  |  | APOKYI KWASI JOSEPH | CANTOMENTS | GPS-940-88 | 0.83 | 40 | FEB
|  |  | KROKOTO EMMANUEL | TAIFA | GPS-356-40 | 0.38 | 60 | MAR
|  |  | STEPHEN OTEIKU | KANESHIE | GPS-751-71 | 0.94 | 80 | APR
|  |  | STEPHEN FOSU | WEIJA | GPS-324-98 | 0.3 | 100 | MAY
|  |  | RICHARD OPPONG | LABONE | GPS-320-88 | 1 |  | JUN
|  |  | AGNES OPPONG | SPINTEX | GPS-455-96 | 2.59 |  | JUL
|  |  | ISAAC ESSOAH | TAIFA | GPS-998-47 | 0.84 |  | AUG
|  |  | DIANA AMUNU | TESHIE | GPS-762-87 | 0.45 |  | SEP
|  |  | SETH BARFO | TAIFA | GPS-459-48 | 0.13 |  | OCT
|  |  | AGANA AMOS AKPALIGABEY | LAPAZ | GPS-784-74 | 0.44 |  | NOV
|  |  | AMUKONA EMMANUEL | DOME | GPS-466-32 | 1.34 |  | DEC
|  |  | SANDRA OWUSU | WEIJA | GPS-177-71 | 0.61
|  |  | CHARLES ANSAH | WEIJA | GPS-659-72 | 0.47
|  |  | GUTAAH KWAKU | TESHIE | GPS-619-90 | 1.09
[7 empty] | name_of_PO | PO_ID | Sector | phone_number
[7 empty] | NANA KWAKU SAFO | A0054 | 1 | 0599917254
[7 empty] | KOJO AMPEM-DARKO | A0251 | 1 | 0550294943
[7 empty] | CELESTINA SACKEY | A0098 | 1 | 0544228198
[7 empty] | NANA KWESI SAFO | A0001 | 1 | 0541836219
Formulas:
Officer ID = IF([house_number]=0,"",J4)

## sample data
owner_name | location | GPS_address | GPS_area | name_of_Officer | Officer _ID | Sector | phone_number
KWAKU BOATENG | LABONE | GPS-902-20 | 0.45 | NANA KWAKU SAFO | A0054 | 1 | 0246937977
KOJO WILLSON | TESHIE | GPS-752-32 | 0.86 | KOJO AMPEM-DARKO | A0251 | 1 | 0241479018
ALIDU BAWA | TAIFA | GPS-752-38 | 1.02 | CELESTINA SACKEY | A0098 | 1 | 0573360947
KWAME BAWA | DOME | GPS-850-16 | 0.54 | NANA KWESI SAFO | A0001 | 1 | 0543550766